## Sheet1
Activities Name | A | B | C | D | E | F | G | H
Activity Description | bar: A
Predecessor | - | A | A | B | B,C | E | D,F | F
Time (Days) | 0 | 7 | 9 | 12 | 8 | 9 | 6 | 5